## EXAMPLE Project Schedule Gantt
PROJECT SCHEDULE TEMPLATE WITH GANTT CHART EXAMPLE
PROJECT NAME |  |  |  | START DATE
Project Alpha |  |  |  | 2025-03-31 |  |  | <-- Enter initial Start Date to populate Timeline dates.
PROJECT MANAGER |  |  |  | END DATE |  |  | OVERALL PROGRESS
Raghu Prakash |  |  |  | MM/DD/YY |  |  | 20%
PROJECT DELIVERABLE Description of project deliverable
|  | TASKS |  |  |  |  | DELIVERABLES |  | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
STATUS | PRIORITY | TASK TITLES | OWNER | START DATE | END DATE | # of Days | DELIVERABLE | % COMPLETE | time axis 2025-03-31 to 2025-08-15
In Progress | HIGH | PROJECT KICKOFF |  | 2025-03-31 | 2025-04-21 | 16 |  | 74.33% | bar: 2025-03-31 to 2025-08-15
Not Started | MED | Schedule kickoff meeting | Brent W. | 2025-03-31 | 2025-04-03 | 4 |  | 33% | bar: 2025-03-31 to 2025-04-03
Complete | MED | Agree on objectives | June T. | 2025-04-02 | 2025-04-18 | 13 |  | 100% | bar: 2025-04-02 to 2025-04-18
In Progress | LOW | P1 Task 3 | June T. | 2025-04-13 | 2025-04-18 | 5 |  | 90% | bar: 2025-04-14 to 2025-04-18
In Progress | LOW | P1 Task 4 |  | 2025-04-03 | 2025-04-12 | 7 |  | 33% | bar: 2025-04-03 to 2025-04-11
On Hold | LOW | P1 Task 5 |  | 2025-04-09 | 2025-04-20 | 8 |  | 100% | bar: 2025-04-09 to 2025-04-18
Needs Review | LOW | P1 Task 6 |  | 2025-04-18 | 2025-04-21 | 2 |  | 90% | bar: 2025-04-18 to 2025-04-21
Needs Update | HIGH | INITIATION |  | 2025-04-22 | 2025-06-23 | 45 |  | 25% | bar: 2025-03-31 to 2025-08-15
Needs Update | MED | Detail requests | June T. | 2025-04-22 | 2025-06-21 | 44 |  | 70% | bar: 2025-04-22 to 2025-06-20
In Progress | MED | Hardware requests | Kirk C. | 2025-04-30 | 2025-05-02 | 3 |  | 60% | bar: 2025-04-30 to 2025-05-02
In Progress | MED | Final resources plan | Jason D. | 2025-05-05 | 2025-06-19 | 34 |  | 20% | bar: 2025-05-05 to 2025-06-19
In Progress | MED | Staffing | Seo F. | 2025-05-06 | 2025-06-03 | 21 |  | 0% | bar: 2025-05-06 to 2025-06-03
In Progress | MED | P2 Task 5 |  |  |  | 0 |  | 0%
In Progress | MED | P2 Task 6 |  |  |  | 0 |  | 0%
In Progress | HIGH | DEVELOPMENT |  | 2025-04-14 | 2025-04-25 | 10 |  | 74.33% | bar: 2025-03-31 to 2025-08-15
In Progress | HIGH | Technical requests | Luiza L. | 2025-04-14 | 2025-04-18 | 5 |  | 33% | bar: 2025-04-14 to 2025-04-18
In Progress | HIGH | DB development | Raghu P. | 2025-04-15 | 2025-04-16 | 2 |  | 100% | bar: 2025-04-15 to 2025-04-16
In Progress | HIGH | API development | Raghu P. | 2025-04-17 | 2025-04-17 | 1 |  | 90% | bar: 2025-04-17
In Progress | HIGH | P3 Task 4 |  | 2025-04-21 | 2025-04-24 | 4 |  | 33% | bar: 2025-04-21 to 2025-04-24
In Progress | HIGH | P3 Task 5 |  | 2025-04-22 | 2025-04-23 | 2 |  | 100% | bar: 2025-04-22 to 2025-04-23
In Progress | HIGH | P3 Task 6 |  | 2025-04-25 | 2025-04-25 | 1 |  | 90% | bar: 2025-04-25
In Progress | HIGH |  |  | 0 | 0 | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  | 0 | 0 | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
END DATE = MIN([END DATE, row below]:F18)
END DATE = MIN(IF([END DATE, row below]:F32="","",[END DATE, row below]:F32))

## BLANK Project Schedule Gantt
KOSS' SCHEDULE WITH GANTT CHART
PROJECT NAME |  |  |  | START DATE
MUFG Projects |  |  |  | 2024-09-02 |  |  | <-- Enter initial Start Date to populate Timeline dates.
PROJECT MANAGER |  |  |  | END DATE |  |  | OVERALL PROGRESS
|  |  |  | MM/DD/YY |  |  | 20%
PROJECT DELIVERABLE Description of project deliverable
|  | TASKS |  |  |  |  | DELIVERABLES |  | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
STATUS | PRIORITY | TASK TITLES | OWNER | START DATE | END DATE | # of Days | DELIVERABLE | % COMPLETE | time axis 2024-09-02 to 2025-01-17
In Progress | HIGH | BONE EOS - Back-end |  |  |  | 0 |  | 50% | bar: 2024-09-02 to 2025-01-17
Complete |  | Java 7 & Gradle migration POC |  | 2024-07-05 | 2024-09-13 | 51 |  | 100% | bar: 2024-09-02 to 2024-09-13
In Progress |  | Workflow Enginee Study (Deadlock issue) |  | 2024-09-13 |  | -32535 |  | 0%
On Hold |  | ~ BONE workflow study |  | 2024-09-13 | 2024-09-27 | 11 |  | 0% | bar: 2024-09-13 to 2024-09-27
Complete |  | ~ Activiti POC (Set up Maven & Single thread) |  | 2024-10-02 | 2024-10-09 | 6 |  | 100% | bar: 2024-10-02 to 2024-10-09
|  | ~ Activiti POC (local SQL & Multi-thread) |  | 2024-10-10 | 2024-11-01 | 17 |  | 100% | bar: 2024-10-10 to 2024-11-01
|  | ~ DB connection |  | 2014-11-01
On Hold |  | ~ Summary Report |  |  |  | 0 |  | 0%
In Progress | HIGH | BONE EOS - Front-end |  |  |  | 0 |  | 0%
In Progress |  | Angular Demo Project (AML) |  | 2024-11-04 |  | -32571 |  | 0%
In Progress |  | Angular sample project deployment guide |  | 2024-11-06 |  | -32573 |  | 0%
[6 empty] | 0 |  | 0%
On Hold |  | Angular (Datetime issue, can we frocely use HKT) |  |  |  | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
In Progress | HIGH | BONE User Guiide |  | 2024-11-02 | 2025-01-15 | 53 |  | 0% | bar: 2024-09-02 to 2025-01-17
In Progress |  | Enviornment Set Up |  |  |  | 0 |  | 0%
Not Started |  | Project Set up |  |  |  | 0 |  | 0%
Not Started |  | Guide for creating simple application |  |  |  | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
In Progress | MED | Development & Support |  |  |  | 0 |  | 66.67%
Not Started |  | NOSQL&Oracle POC | Zechariah Ngai |  |  | 0 |  | 0%
Complete |  | MICR Printer & FlatPC Wellness Check | Can Lau | 2024-11-05 | 2024-11-05 | 1 |  | 100% | bar: 2024-11-05
Complete |  | AutoForm eAdvice Handling - Dev | Zechariah Ngai | 2024-09-20 | 2024-09-23 | 2 |  | 100% | bar: 2024-09-20 to 2024-09-23
Complete |  | AutoForm eAdvice Handling - UAT | Toshitada Kido | 2024-09-23 | 2024-10-09 | 13 |  | 100% | bar: 2024-09-23 to 2024-10-09
Complete |  | STD Monthly roster support |  | 2024-09-01 | 2024-09-30 | 21 |  | 100% | bar: 2024-09-02 to 2024-09-30
[6 empty] | 0 |  | 0%
|  | Other |  |  |  | 0 |  | 16.67%
|  | Leave |  | 2024-10-14 | 2024-10-14 | 1 |  | 0% | bar: 2024-10-14
|  | Holiday (Mid-autumn) |  | 2024-09-18 | 2024-09-18 | 1 |  | 0% | bar: 2024-09-18
|  | Holiday (Oct 1) |  | 2024-10-01 | 2024-10-01 | 1 | bar: 2024-10-01
|  | Leave |  | 2024-11-26 | 2024-12-02 | 5 |  | 0% | bar: 2024-11-26 to 2024-12-02
|  | Leave |  | 2025-01-15 | 2025-01-15 | 1 |  | 0% | bar: 2025-01-15
|  | Beach Clean Up Day Helper |  | 2024-10-14 | 2024-10-18 | 5 |  | 100% | bar: 2024-10-14 to 2024-10-18
|  | Annual Dinner - Local Staff Performance |  | 2024-10-31 | 2025-01-17 | 57 |  | 0% | bar: 2024-10-31 to 2025-01-17

## Dropdown keys - DO NOT DELETE
DROPDOWN KEYS - DO NOT DELETE
STATUS | PRIORITY
Not Started | LOW
In Progress | MED
Complete | HIGH
On Hold
Overdue
Needs Review
Needs Update